## Sheet1
Product Backlog Items
SNo | Priority | ID | Name | Estimated Hours | Authors
1 | 1 | FP_1 | File Parsing | 3 hours | Seif
2 | 1 | VM_1 | View Movies | 1 hour | Homayun
3 | 1 | SMG_1 | Genre Search Method | 2 hours | Faaz
4 | 1 | RM_1 | Rate movies | 3 hours | Seif
5 | 1 | MR_1 | Movie Reccomendation | 3 hours | Zeeshan
6 | 2 | EX_1 | Exit | 1 hour | Homayun
7 | 2 | BKLOG_1 | Format and finish backlogs | 3 hours | All
8 | 2 | READ_1 | Update accurate README | 1 hour | Seif
| 1 | MAIN_1 | Main.java file (Core App logic) | 3 hour | All
Note: The details of Each PBI is provided in new sheets of this document with the ID of the PBI as the title of the sheet.

## FP_1
PBI
ID | FP_1
Name | File Parsing
Description | File Parsing system that allows us to parse data successfully and handle errors gracefully
Acceptance Criteria | 1. (Successful Parse): Valid files must load all movies and ratings into memory correctly. 2. (Error Handling): Malformed lines are skipped and logged without terminating execution. 3. (Validation): All numeric fields must be validated before insertion (e.g., rating must be an integer 1–5). 4. (Empty File): If a file is empty or missing, the system must display a readable error message."
2. (Error Handling): Malformed lines are skipped and logged without terminating execution.
3. (Validation): All numeric fields must be validated before insertion (e.g., rating must be an integer 1–5).
4. (Empty File): If a file is empty or missing, the system must display a readable error message."
Definition of Done | Files are parsed correctly and tested
Estimated Effort | Medium difficulty with around 3 hours work time
PBI Author | Seif

## VM_1
PBI
ID | VM_1
Name | View Movies
Description | Users can view all movies, sorted and organized
Acceptance Criteria | Users can view all movies, sorted and organized according to requirements and filtering
Definition of Done | errors are handled gracefully, and edge cases are tested to ensure different input types are accepted
Users can view movies, sorted and filtered according to input,
Estimated Effort | 1 hour
PBI Author | Homayun

## EX_1
PBI
ID | EX_1
Name | Exit System
Description | Exit System that allows users to successfully exit the program, errors handled gracefully
Acceptance Criteria | Users can successfully exit, errors are handled gracefully as per assignment reqs.
Definition of Done | Exiting is seamless and errors are handled
Estimated Effort | Easy difficulty with around 1 hour work time
PBI Author | Homayun

## READ_1
PBI
ID | READ_1
Name | Update README file
Description | Root level Readme file
Acceptance Criteria | Readme accurately reflects compilaiton instructions and nicely formatted
Definition of Done | Readme is updated and accurate
Estimated Effort | Easy difficulty, 10 minutes max
PBI Author | Seif

## BKLOG_1
PBI
ID | BKLOG_1
Name | Update backlogs and finialize
Description | product and Sprint backlogs
Acceptance Criteria | Backlogs are updated (constantly) and accurately reflect work
Definition of Done | Backlogs are finished with up-to-date PBI's reflecting work and effort
Estimated Effort | Easy difficulty, Updated constantly so no set time
PBI Author | Seif, Faaz, Zeeshan, Homayun

## RM_1
PBI
ID | RM_1
Name | Rate Movies
Description | Allow users to update a Movie's rating
Acceptance Criteria | 1. (Valid Input): Users can only enter ratings between 1 and 5.
2. (Update Existing): If a user re-rates a movie, the previous rating is replaced.
3. (Error Handling): If a movie ID does not exist, the system must display a clear error message.
4. (Persistence): Updated ratings must be reflected immediately in the system and available for other
Definition of Done | Users can successfully rate movies, all edge cases are accounted for and tested
Estimated Effort | Low-Medium difficulty max 3 hours work time
PBI Author | Seif

## MR_1
PBI
ID | MR_1
Name | Recommendation Engine Implementation
Description | Implement the full content-based filtering logic. This includes calculating similarity scores between highly-rated and unwatched movies, and implementing the necessary fallback for cold-start users.
Acceptance Criteria | 1. (Cold Start): When the user has zero ratings, the system displays the top 10 most popular movies, sorted by avg_rating then by num_ratings 2. (Similarity Score): When the user has rated >= 1 movie with 4 or 5 stars, the system must generate recommendations based on genre overlap with those films. 3. (Filtering): Recommended movies must never include titles the user has already rated. 4. (Normalization): The similarity calculation must correctly match genres ('Sci-Fi' vs. 'scifi') to ensure accurate scores.
Definition of Done | 1. MovieRecommendationAlgorithm.java is implemented and calculating similarity 2. DataManager.getPopularMovies() is implemented and correctly using the tie-breaker sorting logic 3. All associated Unit Tests for the similarity method have been written and passed 4. System Test Cases for Cold Start and Similarity have been designed and executed 5. Code has been integrated and merged with the main branch.
Estimated Effort | 6 hours
PBI Author | Zeeshan Bombaywala

## MAIN_1
PBI
ID | MAIN_1
Name | Main.java implementation (Core app implementation)
Description | Implement the core app logic for main.java, CLI implementation.
Acceptance Criteria | Options invoke components (1=view,2=rate,3=search,4/5="Coming soon",6=save & exit)
; non-exit choices pause with "Press Enter to continue..." and return to menu.
Prints welcome + menu (1–6); only accepts "1"–"6" (invalid/EOF reprompt).
Definition of Done | Compiles on Java11+, manual tests for each menu flow pass, ratings persisted on exit, scanner closed,
no unhandled exceptions, app handles missing data files gracefully.
Estimated Effort | 5 hours
PBI Author | Faaz, Seif, Zeeshan, Homayun

## SMG_1
PBI
ID | SMG_1
Name | Search Movies By Genre Implementation
Description | Implemented full search algorthim based on user's genre input. This includes correctly parsing user's inputs to satisfy the correct movies in CSV files, and constructing the logic for the search algoritihim
Acceptance Criteria | 1. When the user will select "Searhc Movie by Gere" from the CLI and enteres a valid genre from the CSV file, the system will result in displaying the correct movies 2. The search for movies is case-insensitve, meaning the user input will directly map to the movies in the CSV file even with non-matching capilization3. 3. If user inputted movies do not match any movies in the CSV files, then there will be a specifc prompt denoting such to the user
Definition of Done | 1. A search by genre method is correctly implemented, where user input of the genre will correctly output associated movies 2. All test cases are covered: valid genres, genres with multiple movies, genres with no matched, user case-insensitive and valid/unvalid user inputs 3. The CLI option for "Search Movies by Genre" is fully connected to the implementation java file 4. All SDD/SRS requiemnts are implmentated into the section, following the correct logic and criteria
Estimated Effort | 6 Hours
PBI Author | Faaz Shaikh